## Slide 1
Product Development Process
RACI Responsibility Matrix · Discovery through MP Launch
R Responsible
A Accountable
C Consulted
I Informed
R/A Both

## Slide 2
Development Phases at a Glance
Discovery
Worth deeper investment?
›
Concept
Should we invest further?
›
EVT Entry
Design mature for EVT?
›
EVT
Freeze arch → push to DVT?
›
DVT Entry
Arch mature? Test plan ready?
›
DVT
Pass validation & certification?
›
PVT Handover
Factory ready for PVT?
›
PVT
Final BOM, certs, training
›
MP / Launch
Sustain or retire mode?
★ Gate reviews (Go / No-Go / Hold / Pivot) required at the end of each major phase
Roles: SVP · Eng Directors · Project Management · Mechanical Eng · Electrical Eng · Firmware Eng · ID/UX · Product Development · Quality/Manufacturing · Operations
R Responsible
A Accountable
C Consulted
I Informed
R/A Both

## Slide 3
Discovery Phase
Is this worth real concept work and deeper investment?
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Conduct Innovation Sessions | I | I | R | C | C | C | C | A |  | 
Competitive Benchmarking | I | I | I | R | R | R | I | A | I | 
Technical Feasibility Assessments |  | A | I | R | R | R |  | I | C | 
Bench Top Concepts |  | A | I | R | R | R | I | I |  | 
Platform Assessment | I | A | I | R | R | R |  | C |  | 
System Mapping |  | A | I | R | R | R | I |  |  | 
Pre-BOM Inputs |  | A | I | R | R | R |  | I |  | C
Past Problem History | I | I | I | I | I | I | I | I | R/A | I
Scope Regulations & Compliance |  | C | I | C | C | C |  | R/A | I | I
Initial Make vs Buy Analysis | I | C | I | C | C | C |  | C |  | R/A
IP Assessment |  | C | I | C | C | C | C | I |  | R/A
★ Discovery Exit Gate Review | A | R | R | R | R | R | R | R | R | R

## Slide 4
Concept Phase
Develop the idea to give the business clarity — should we invest further?
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
ID Refinement |  | C | I | C | C |  | R/A | C |  | 
3D Print Evaluation | C | A | I | R |  |  | C | C |  | 
Initial CAD Assessment |  | A | I | R | C |  | C |  |  | 
Initial Failure Simulations |  | A | I | R |  |  |  |  |  | 
Initial DFM Review | I | R/A | I |  |  |  |  | C | C | 
Schematic Outline |  | C | I | I | R/A | C |  |  |  | 
Preliminary PCB Layout |  | C | I | I | R/A | C |  |  |  | 
Initial Firmware Development |  | I | I |  |  | R/A |  |  |  | 
Preliminary DFMEA |  | A | I | R | R | R |  | C | C | 
Risk Register Established | I | C | R/A |  |  |  | C | C | C | 
★ Concept Exit Gate Review | A | R | R | R | R | R | R | R | R | R

## Slide 5
EVT Entry Expectations
Do we have the required scope and is the design mature enough to begin EVT?
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Concept Agreement | C | R/A | I | C | C | C | R | C |  | 
BOM Review Complete |  | R/A | I | C | C | C |  | I | C | C
EVT Build Plan |  | R/A | I | C | C | C |  |  | C | C
Concept CAD Frozen |  | A | I | R | C | C |  |  |  | 
Schematic Frozen |  | C | I |  | R/A | C |  |  |  | 
Contract Manufacturing Confirmed | I | C |  |  |  |  |  | C |  | R/A

## Slide 6
EVT Phase
Progressing design towards full validation and tooling release.
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Hardware Bring-Up |  | A | I |  | R | C |  |  |  | 
Firmware Development |  | A | I |  | C | R |  |  |  | 
Electrical Pre-Scan |  | A | I |  | R |  | I | I |  | 
Assembly Verification |  | A | I | R |  |  |  |  | C | 
DFM Finalized |  | A | I | R |  |  |  |  | C | I
EoL Development |  | A | I |  | C | R |  | I | I | 
System Architecture & Feature Alloc. |  | A | I | R | R |  |  |  |  | 
DFMEA & Test Matrix Updated |  | R/A | I | C | C | C |  |  | C | C
Risk Register Updated | I | C | R/A |  |  |  |  |  | C | C
CM Reporting Cadence Agreement |  | C | R/A |  |  |  |  |  | C | C
EVT Build | I | R/A | I |  |  |  |  |  | C | C
★ EVT Exit Gate Review | A | R | R | R | R | R | R | R | R | R

## Slide 7
DVT Entry Expectations
Is the system architecture mature? Do we have a confirmed test plan?
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Design Status – Frozen | I | A | R | C | C | C | C | C | C | C
Feature Functionality Complete |  | A | I | R | R | R |  | C |  | 
Tooling Agreement | C | C | R |  |  |  |  |  | C | A
BOM Review Complete |  | R/A | I | C | C | C |  | I | C | C
EVT Test Report Documented |  | A | I | R | R | R |  |  | C | 
Certification Plan Documented | I | C | R/A |  |  |  |  | I | C | C
Yield Report Reviewed | I | I | I |  |  |  |  |  | R/A | C

## Slide 8
DVT Phase
Progressing towards production level builds that can pass all validation and certification.
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Tooling Validation | I | C | I |  |  |  |  |  | R/A | C
Reliability Testing |  | C | I |  |  |  |  |  | A | R
Process Flow Diagram Development |  | I | I |  |  |  |  |  | R/A | 
Establish Work Instructions |  | I | I | C | C | C |  |  |  | R/A
Develop PFMEA |  | R | I | C | C | C |  | A | C | 
Write Control Plan & Production Docs |  |  | I |  |  |  |  |  | R/A | C
Determine Cosmetic Limit |  | C | I |  |  |  | C |  | R/A | C
DVT Build | I | R/A | I |  |  |  |  |  | C | C
DVT Testing | I | R/A | I |  |  |  |  |  | C | C
Regulatory Certification |  | A | R |  |  |  |  | I |  | 
Confirm Firmware Stability |  | I | I |  |  | R/A |  |  |  | 
Yield Analysis |  | I | I |  |  |  |  |  | R/A | C
Packaging Testing |  |  | I |  |  |  |  |  | R/A | 
★ DVT Exit Gate Review | A | R | R | R | R | R | R | R | R | R

## Slide 9
DVT to PVT Handover
Have we identified all engineering risks and provided support needed for manufacturing?
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Tooling Approval |  | C | I |  |  |  |  |  | R/A | 
Regulatory Certifications Confirmed |  | A | R |  |  |  |  | I |  | 
Reliability Test Report Reviewed | I | R/A | I |  |  |  |  |  | C | C
Firmware Release Candidate Ready |  | I | I |  |  | R/A |  |  | C | C
Quality Plan Reviewed |  |  | I |  |  |  |  |  | R/A | 
Run at Rate Validation |  | I | I |  |  |  |  |  | R/A | C
Target Yield Met |  | I | I |  |  |  |  |  | R/A | C
★ PVT Handover Gate Review | A | R | R | R | R | R | R | R | R | R

## Slide 10
PVT Phase
Supporting activities: final BOM, certifications, PFMEA, work instructions.
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Final Component Cost Analysis |  | R/A | I | C | C | C |  | I | C | C
PVT Build Complete | I | R/A | I |  |  |  |  |  | C | C
Yield Root Cause Analysis |  | I | I |  |  |  |  |  | R/A | C
Limit Sample Tuning |  | C | I |  |  |  |  |  | R/A | C
Maintain Firmware Stability |  | I | I |  |  | R/A |  |  | C | 
Develop Service Manual / Repair Guide |  | R/A | I |  |  |  | C | I |  | 
Technical Training |  | R/A | I |  |  |  | C | I |  | 
Complete After Action Review | C | C | R/A | C | C | C | C | C | C | C

## Slide 11
MP / Launch Exit Phase
Are we moving from growth/launch into sustain/retire mode intentionally?
R
A
C
I
R/A
Activity | SVP | Eng Dir | PM | Mech | Elec | FW | ID/UX | Prod Dev | Q/Mfg | Ops
Product Support / Sustainment Plan | A | R | I |  |  |  |  | C | C | C